REPUBLIC OF SOUTH AFRICA

IN THE HIGH COURT OF SOUTH AFRICA GAUTENG LOCAL DIVISION, JOHANNESBURG

CASE NUMBER: 45879/2018

In the matter between:

GROUP FIVE CONSTRUCTION (PTY) LTD	Applicant

and

TRANSNET SOC LIMITED	Respondent

# SUMMARY

- This matter involves a written agreement between the parties in terms of which the respondent contracted the applicant for the provision of various work on a coastal terminal. The agreement included several provisions on dispute resolution in terms of which the parties agreed that any dispute arising under or in connection with the contract would be referred to and decided by an independent adjudicator. Over and above this, the parties agreed on the following:

- The adjudicator would decide the dispute and notify the parties of his decision and his reasons within four weeks of the end of the period for receiving information but this four week period could be extended if the parties agreed.

- Should the adjudicator fail to notify the parties of his decision within this agreed timeframe, a party could notify the other party of its intention to refer the dispute to the appointed tribunal.

- A dispute subsequently arose between the parties pertaining to the respondent's issuance of a final payment certificate. This dispute was referred to an adjudicator and the parties accordingly submitted all necessary information. However, following the conclusion of the four week period, the adjudicator requested an additional seven calendar days to finalise a request for further information after which he would be in a position to finalise his award within four weeks. The respondent refused to grant the adjudicator this extension and gave notice to the applicant of its intention to refer the dispute to the tribunal. The respondent also informed the adjudicator that its notice to refer the dispute to the tribunal was final and that the adjudicator's intention to proceed was at his peril. However, the adjudicator continued to communicate and received certain information from the applicant without any further contribution and participation from the respondent and subsequently published his decision.

- The issue necessary for the Court to consider was whether the decision of the adjudicator was binding and enforceable even though the respondent had refused consent to extend the time of its publication. The applicant submitted that the Court was not competent to preside over matters which are in the domain of the arbitrator. Furthermore, the applicant submitted that whilst the decision of the adjudicator was late, it was not provided in the contract that it would be invalid if issued after the four week period. The respondent submitted that time was of the essence in building contracts hence the agreement between the parties to resolve their disputes by way of adjudication before referring the matter to arbitration. The respondent further contended that by filing a notice to refer the dispute to arbitration, it put a stop to the adjudication process and disempowered the adjudicator from continuing with the process.

- Citing Lufuno Mphaphuli & Associates (Pty) Ltd v Nigel Athol Andrews & Another and Radon Projects (Pty) Ltd v NV Properties (Pty) Ltd &: Another, the Court acknowledged that it is a trite principle in the law that the Courts should be slow in entertaining issues which fall squarely in the domain of the arbitrator or adjudicator in terms of an agreement concluded between the parties.

- Relying on Novartis v Maphil, the Court recognised that in order to determine the issue of whether the decision of the adjudicator was binding and enforceable, it would have to examine the contract concluded between the parties as well as all background facts and circumstances under which the contract was concluded. The Court stated that the starting point when interpreting any document must be the words of the document as well as the intention of the parties.

- The Court agreed with the respondents that time is of the essence in building contracts of this nature - hence the provision that disputes between parties are referred to adjudication for speedy settlement. The Court ultimately concluded:

"[T]he time period for the publication of the adjudicator's decision is 4 weeks from the date when he receives the last submissions from the parties, unless the parties agree to grant him an extension of time. These clauses do not state what should happen when a party does not grant the consent to extend the period. I am of the respectful view that the intention of the parties to make the requirement of consent from the parties to afford the adjudicator more time is meant to give the parties control over the process of the adjudication. It is meant to give the parties some power to deal, should they find themselves in that situation, with a recalcitrant adjudicator. The ineluctable conclusion is therefore that, absent such consent to the extension of time, the adjudicator should publish his report on due date failing which his mandate is terminated. I am therefore unable to disagree with counsel for the respondent that, from the plain wording of these clauses, the adjudicator is not competent to proceed and act beyond the time period set by the agreement if he is unable to secure the necessary consent from both parties. No other meaning can be ascribed to these provisions for they are not at all ambiguous."

- The Court held that the decision of the adjudicator was published late and in breach of the terms of the agreement and was therefore not binding and enforceable against the respondent.

- The application was dismissed with costs.

2009 (4) SA 529 (CC).

2013 (6) SA 345 (SCA).

2016 (1) SA 518 (SCA).

At para [21] of the judgment.